{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":67,"n_cols":13,"rows_kept":67,"merged":[[0,0,0,12],[1,0,3,0],[1,1,3,1],[1,2,3,2],[1,3,1,4],[1,5,3,5],[1,6,3,6],[1,7,3,7],[1,8,2,9],[1,10,3,10],[1,11,3,11],[1,12,3,12],[2,3,3,3],[2,4,3,4]],"flags":["formulas_cached_only"]}
["2024年度巩固拓展脱贫攻坚成果和乡村振兴项目计划安排表"]
["序号","项目名称","项目摘要\n（建设内容及规模）","项目实施地点",null,"规划年度","实施\n单位","项目预算  总投资 （万元）","受益\n脱贫户人口",null,"受益总人口","绩效目标","备注"]
[{"$nulls":3},"镇/办","村/社区"]
[{"$nulls":8},"户数\n(户)","人数（人）"]
[null,"产业发展类",{"$nulls":5},5054.514]
[1,"代王街道代王村肉兔养殖产业设施建设项目","两个六连体兔舍，（六连体商品兔舍尺寸50米X82.08米X2个=8208平方），种兔兔舍一个（38米X6.5米＝247平方）.共计兔舍13个8455平方米；兔笼102组。","代王街办","代王村",2024,"代王街办",976.594,7,20,1680,"壮大集体经济，逐步实现村级乡村振兴"]
[2,"油槐街道公共屋顶光伏项目","安装光伏1089KW及相关配套设施。","油槐街办","石家、余家、耿西、南杨、 白家、 南张",2024,"油槐街办",453.92,79,160,16563,"改善农民生活要求，同时增加了村集体和村民收入。"]
[3,"小金街道小金村屋顶光伏项目","小金村中心小学及卫生室等屋顶安装光伏1026KW","小金街办","小金村",2024,"小金街办",470,170,635,2433,"带动产业发展，壮大村集体经济"]
[4,"小金街道炮岭村方园产业园提升项目","新建冷库仓储100吨，修建砂石路4500平方米，倒勾喷灌100亩，分装棚150平方米及配套相关设施","小金街办","炮岭村",2024,"小金街办",110,34,162,1133,"带动产业发展，壮大村集体经济"]
[5,"相桥街道神东村肉牛标准化养殖场建设项目"," 新建标准化牛舍4800平方米； 新建青储窖、饲料间、原料间1000平方米。","相桥街办","神东村",2024,"相桥街办",403,10,27,2023,"增加村集体收入，带动群众增收"]
[6,"相桥街办姚家村粮食储备库建设项目","新建标准化粮食储备库6000平方米，粮食烘干设备1套及转运机械3台。","相桥街办","姚家村",2024,"相桥街办",580,22,55,1960,"增加村集体收入，带动群众增收"]
[7,"徐杨街道徐杨村肉牛养殖项目","两栋5600平方米养殖大棚及养殖配套设施","徐杨街道","徐杨村",2024,"徐杨街办",280,17,52,3500,"项目建成后预计带动村集体收益15-20万元。"]
[8,"铁炉街道铁炉村冷库仓储及配套设施项目","建设400吨冷库，添置果框、托盘、叉车等设备","铁炉街办","铁炉村",2024,"铁炉街办",395,30,84,2390,"带动产业发展，提高当地群众收益"]
[9,"何寨街道河西村肉兔养殖配套设施项目","建设兔棚8个，笼具538套；传送带3套；收集传送带系统1套；温控灯带8套；水帘通风16套；风机40个；棚内硬化480O平方；硬化道路200米；仓库260平方米及配套室200平方米。","何寨街办","何寨辖区",2024,"何寨街办",456,40,62,3000,"带动产业发展，提高当地群众收益"]
[10,"雨金街道东关村番茄大棚及相关基础建设项目","建设长100米、宽16.5米、高6米的新型钢架结构温室大棚15座，配套监测系统、智能放风机、电动卷膜设备、水肥一体化系统、滴管系统、高压雾化系统、补光系统、物联网系统及农作物指标检测等系统。棚间配套灌溉管网、电路管网并辅助生产砂石道路等配套设施.","雨金街办","东关村",2024,"雨金街办",900,6,9,1800,"带动产业发展，提高当地群众收益"]
[11,"2024年全区小额信贷贴息","2024年全区小额信贷贴息","全区",null,2024,"区金融办",30,300,1000,3000,"促进群众发展产业，增加群众收入"]
[null,"安全饮水类",{"$nulls":5},170.2]
[1,"2024年全区农村安全饮水工程水质检测","全区160处农村安全饮水工程水质检测","全区",null,2024,"区水务局",24,5200,15000,500000,"保障全区农户饮水水质安全"]
[2,"仁宗街道芋坡村人畜饮水项目","新建拦水坝1座，新建80方蓄水池1座，铺设管道4000米，水泵1个.架设电力设备，在张南帮新建20方蓄水池3个。","仁宗街办","芋坡村",2024,"仁宗街办",120,50,200,280,"解决群众人畜饮水问题"]
[3,"穆寨街道三庙村饮水管网改造及提升项目","修建围墙长100米，新建管理房一间30平方，新修蓄水池一座，埋管道1200米。","穆寨街道","三庙村",2024,"穆寨街道",26.2,241,919,919,"方便群众用水"]
[null,"基础设施类",{"$nulls":5},4695.5273]
[1,"穆寨街道损毁道路修复项目","东岳村35米悬空砌挡墙修复；西岳村姚家组砌挡墙120米；门岩村悬空修复砌挡墙150米，路面修复硬化100米；三庙村损毁路面硬化200米，悬空砌挡墙300米。业池村通村路悬空路修复，砌挡墙300米。","穆寨街道","穆寨辖区",2024,"穆寨街道",260.5,877,2317,8612,"修复损坏道路，修建挡墙，确保群众安全"]
[2,"仁宗街道水毁修复项目","修复路面14000平方米，砌石200立方米，排水渠1000米","仁宗街办","仁宗辖区",2024,"仁宗街办",350,170,500,800,"解决群众道路出行问题，保障群众出行安全"]
[3,"毛湾村民俗配套设施建设项目","毛湾村道路道路翻修及会车点增设5.5km，毛湾村毛西组新修雨水污水处理及排放1处，新建灌溉井1座及管网，电力扩容等。","小金街办","毛湾村",2024,"小金街办",350.9,20,60,525,"提升基础设施建设，改善人居环境，促进乡村振兴"]
[4,"西泉街道东赵村道路修复及排水项目项目","主干路硬化13500平方米，两侧排水2700米","西泉街办","东赵村",2024,"西泉街办",245,13,36,3424,"改善人居环境，提升出行条件"]
[5,"新市街道焦范村道路排水设施建设项目","雨水管网450米，雨污管网420米，道路硬化5200平方米。","新市街办","焦范村",2024,"新市街办",142,13,35,2738,"改善人居环境，提升出行条件"]
[6,"相桥街道北刘村南刘组道路及排水设施提升改造项目","道路硬化5600平方米(其中4米宽道路900米，5米宽道路400米)；铺设排水暗管800米","相桥街办","北刘村",2024,"相桥街办",152,1,5,2437,"提升基础设施建设，改善人居环境，促进乡村振兴"]
[7,"代王街道山任村基础设施道路水毁项目","新建砌石挡墙5处，道路修复115平方米。","代王街办","山任村",2024,"代王街办",140,24,89,2316,"改善人居环境，提升出行条件"]
[8,"秦陵街道乡村旅游临代路改造项目","道路黑化16800平方米（路宽），排水渠2800米","秦陵街办","秦陵村",2024,"秦陵街办",460,"1","1",4316,"提升基础设施建设，改善人居环境，促进乡村振兴。"]
[9,"雨金街办重点帮扶镇二期建设项目","雨金东西街道--道路新砌仿石道沿1392米；道路黑化，长687米，宽9米，共计6183平方；安装太阳能路灯46套；拆除、清运原路灯、广告牌、树池（树木）；破损行道修复、基本绿化等。","雨金街办",null,2024,"雨金街办",200,140,351,23347,"持续推进人居环境综合整治及基础设施提质更新行动，进一步提升群众获得感、幸福感增强。"]
[10,"胡张村基础设施提升改造项目","安庆组入组路道路硬化工程，宽4米，厚18厘米，长800米。","栎阳街办","胡张村",2024,"栎阳街办",50,3,3,856,"提高基础设施建设，巩固脱贫攻坚成果，全面提升村容村貌，建以宜在宜业村庄。"]
[11,"齐家村基础设施提升改造项目","新兴组修复破损路面700平方米，修复村道“300”螺纹管排水1200米。\n","栎阳街办","齐家村",2024,"栎阳街办",50,5,8,2532,"提高基础设施建设，巩固脱贫攻坚成果，全面提升村容村貌，建以宜在宜业村庄。"]
[12,"零口街道大寨村排水设施提升项目","对寨东至寨西铺设排水管道1600米，对路两边600米路沿进行石材铺设。","零口街办","大寨",2024,"零口街办",50,12,39,2598,"方便群众出行条件，改善人居环境，提升群众生活幸福指数\n"]
[13,"马额街道荣村道路硬化项目","1.路面硬化长600米，宽4米，共计2400平方米；2.旧路面破碎及拉运2400平方米。","马额街办","荣村",2024,"马额街办",52,15,44,1863,"改善路域环境和通行质量，提升群众出行便捷度，带动建档立卡户15户44人，全村1863人受益。提升群众生活幸福指数和满意度。\n"]
[14,"新丰街办皂安村委至岩赵组、温家组、贾家组道路维修项目","道路长700米，宽4米，共2800平方米。","新丰街办","皂安村",2024,"新丰街办",58.76,12,34,3473,"改善群众出行，提高群众生活质量"]
[15,"秦陵村道路基础设施建设项目","临马路至秦陵小学道路沥青铺设：全长708米，总面积3416平方米","秦陵街办","秦陵村",2024,"秦陵街办",53.6,1,1,4816,"改善群众出行，提高群众生活质量，全面提升村容村貌"]
[16,"鱼池村道路硬化项目","道路硬化全长772米，总面积2403平方米,其中吴西组1161平方米，吴中组262平方米，吴东组980平方米","秦陵街办","鱼池村",2024,"秦陵街办",54,1,1,2752,"改善群众出行，提高群众生活质量，全面提升村容村貌"]
[17,"三王村一组道路提升项目","道路拓宽，土方清理5000米，3750立方，路基处理3750平米，太阳能路灯安装50盏。","任留街办","三王村",2024,"任留街办",50,12,40,1959,"方便群众出行，带动村民经济发展"]
[18,"斜口街道韩峪村道路硬化工程","范庄组道路硬化600米，马家组道路硬化170米，宽4米，总面积3080平方米。","斜口街办","韩峪村",2024,"斜口街办",53,21,55,3160,"项目建成后，将改善范庄组、马家组道路环境及通行质量，方便群众出行，提升群众生活质量。"]
[19,"余家村道路硬化项目","新建道路3409平方米","油槐街办","余家村",2024,"油槐街办",57,7,32,670,"改善群众出行，提升村容村貌。带动脱贫人口  16户25人，受益总人口3158人。"]
[20,"何寨街道圣力寺村基础设施提升建设项目","拟对圣八组、圣九组、圣五组、硬化道路2120.8平方米，新建排水渠869.8米，地下排水管修复7处29.4米。","何寨街办","圣力寺村",2024,"何寨街办",59,16,25,3158,"改善人居环境，方便群众出行"]
[21,"巨合村永兴组道路硬化项目","道路硬化全长770米，宽度4米，厚度0.18米","徐杨街办","巨合村",2024,"徐杨街办",50,45,130,4100,"改善群众出行，提高群众生活质量，全面提升村容村貌"]
[22,"马庄村基础设施提升改造项目","马西组路道路硬化工程面积2600平方米，雨水管网300米。","新市街办","马庄村",2024,"新市街办",51,1,4,2820,"改善人居环境，方便群众出行。"]
[23,"焦范村基础设施提升改造项目","楼南组雨污管网110米，检测井27眼，兴丰组和三合组道路硬化1920平方米","新市街办","焦范村",2024,"新市街办",50.6,19,62,3567,"改善人居环境，方便群众出行。"]
[24,"新民村基础设施提升项目","铺设排水管网900米，道路硬化324平方米。","交口街办","新民村",2024,"交口街办",50.2,13,35,2738,"提升村容村貌"]
[25,"高铁村余家通村路道路硬化项目","硬化道路2200平方米","交口街办","高铁村",2024,"交口街办",50.6,29,82,4014,"提升村容村貌"]
[26,"营仁村团庄道路提升项目","硬化道路2100平方米，路灯安装10盏。","交口街办","营仁村",2024,"交口街办",50.25,13,25,1975,"提升村容村貌"]
[27,"临潼区相桥街办北孙村孙南组孙北组主干道污水管网工程","沿村道水泥路两侧铺设DN400波纹管200米，铺设DN300波纹管890米；建集水井50座，污水检查井2座；污水管网上方修复水泥路长1090米，宽0.3-0.5米。砖砌花墙孙南组380米，孙北组700米。","相桥街办","北孙村",2024,"相桥街办",50,10,26,1796,"提升基础设施建设，改善人居环境，促进乡村振兴"]
[28,"临潼区相桥街办铁王村主干道加宽及村道新修工程","铁王村主干道扩宽硬化路面580米长，4.5米宽；贤一组村道新修硬化路面70米长，3.5米宽。","相桥街办","铁王村",2024,"相桥街办",50,2,8,1990,"提升基础设施建设，改善人居环境，促进乡村振兴"]
[29,"铁炉村产业路硬化项目","硬化产业路2585平方米","铁炉街办","铁炉村",2024,"铁炉街办",50.0973,9,19,1982,"带动产业发展，提高当地群众收益"]
[30,"门家村门南组和南李组产业路硬化","门家村门南组和南李组产业路硬化，门南组需要硬化产业路长350米，宽3.5米，1225平方米，南李组需要硬化产业路260米，宽3.5米，910平方米，硬化门南组和南李组产业路总计2135平方米，","代王街办","门家村",2024,"代王街办",55,30,84,2390,"方便群众安全出行和生产便利"]
[31,"神东村农村道路建设","北王组至神东组主干道沥青路面长2167米，宽5米。","相桥街办","神东村",2024,"相桥街办",130.02,10,27,2023,"改善群众出行，提升人居环境"]
[32,"山任村山魏组到柿子园通村路","道路修整1099m²,陡崖护栏314m，沥青路面2926.5m，路缘石1742m²。","代王街办","山任村",2024,"代王街办",130,24,89,2316,"加强道路安全，提升该道路。"]
[33,"杨家村人居环境整治整治","1.拆除混凝土路面965平方米，开挖沟槽940立方米；2.垃圾外运1400立方米；3.管道垫层292立方米；4.沟槽土方回填550立方米；5.新建检查井64座，DN300HPDE双壁波纹管铺设965米，DN150PVC管铺设160米；6.沟槽混凝土面层恢复950平方米；7.沙回填430立方米；8、石灰稳定土965平方米。","秦陵街办","杨家村",2024,"秦陵街办",130,4,9,3064,"改善群众生活环境"]
[34,"杨家村农村基础设施改造","1.混凝土道路修复加宽2000平方米，厚度18厘米，2.沥青道路铺设4500平方米，厚度6厘米。","秦陵街办","杨家村",2024,"秦陵街办",130,9,10,3674,"改善群众出行"]
[35,"刘寨村人居环境整治","排污管网3770米一期","新丰街办","刘寨村",2024,"新丰街办",130,8,14,1828,"改善群众生活环境"]
[36,"贾村农村基础设施建设","通村路改造7770㎡","西泉街办","贾村打",2024,"西泉街办",130,3,3,2160,"改善群众出行"]
[37,"零塬村污水管网改造","污水管道1000米及相关配套设施","零口街办","零塬村",2024,"零口街办",130,5,11,2543,"方面群众出行，改善了之前村内污水横流的情况"]
[38,"照渠村道路扩宽硬化，绿化，污水管网工程","街道扩宽硬化2000米，绿化1500米，污水管网工程1520米","雨金街办","照渠村",2024,"雨金街办",130,25,81,3040,"给村民生产生活及出行带来安全方便"]
[39,"石家村基础设施提升改造","1个村民小组道路拓宽、房屋立面改造、绿化等基础设施","油槐街办","石家村",2024,"油槐街办",130,8,18,1738,"提升村容村貌，打造宜居村庄"]
[40,"宋家村基础设施提升","拆除旧进户坡道、拓宽村道4300平米","代王街办","宋家村",2024,"代王街办",130,16,33,3827,"提升村容村貌，打造宜居村庄"]
[null,"其他类",{"$nulls":5},776]
[1,"2024年雨露计划学生补助","2024年全区雨露计划补助","全区",null,2024,"区乡村振兴局",100,300,300,300,"扶持脱贫家庭子女受教育"]
[2,"2024年跨省务工补贴","2024年跨省务工补贴","全区",null,2024,"区乡村振兴局",20,400,400,400,"解决脱贫人口跨省务工交通补助"]
[3,"防返贫监测预警平台","防返贫监测预警平台服务费","全区",null,2024,"区乡村振兴局",66,{"$nulls":3},"有效做好防返贫预警监测"]
[4,"2024年项目管理费","2024年全区项目管理费","全区",null,2024,"区乡村振兴局",590,{"$nulls":3},"确保项目推进程序完善"]
["合计",{"$nulls":6},10696.2413]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}